## Blad1
Projectnaam | User story # | Work item # | Day 5 - remaining hours | Day 4 | Day 3 | Day 2 | Day 1
Sprint 1 | User story 1 | Work item 1.1 | 2 | 2 | 1 | 1 | 0 | Make sure you fill in "hours remaining"
Sprint 1 | User story 1 | Work item 1.2 | 2 | 2 | 1 | 1 | 0
Sprint 1 | User story 2 | Work item 2.1 | 2 | 2 | 1 | 1 | 0
Sprint 1 | User story 2 | Work item 2.2 | 2 | 2 | 1 | 1 | 0
Sprint 1 | User story 3 | Work item 3.1 | 1 | 1 | 0 | 0 | 0
Sprint 1 | User story 4 | Work item 4.1 | 1 | 1 | 0 | 0 | 0
Sprint 1 | User story 5 | Work item 5.1 | 1 | 1 | 0 | 0 | 0
|  | Ideal | 30 | 23 | 16 | 9 | 2
|  | Actual | 30 | 11 | 4 | 4 | 0