## Blad1
Projectnaam | User story # | Work item # | Day 5 - remaining hours | Day 4 | Day 3 | Day 2 | Day 1 | Comment
Sprint 3 | User story 12 | Work item 12.1 | 2 | 1 | 0 | 0 | 0 |  | Make sure you fill in "hours remaining"
Sprint 3 | User story 12 | Work item 12.2 | 2 | 1 | 0 | 0 | 0
Sprint 3 | User story 14 | Work item 14.1 | 4 | 2 | 1 | 0 | 0
Sprint 3 | User story 14 | Work item 14.2 | 4 | 3 | 2 | 1 | 0
Sprint 3 | User story 17 | Work item 17.1 | 6 | 4 | 2 | 1 | 0
Sprint 3 | User story 18 | Work item 18.1 | 3 | 1 | 0 | 0 | 0
|  | Ideal | 30 | 23 | 16 | 9 | 2
|  | Actual | 30 | 12 | 5 | 2 | 0